## Slide 1: CIBC6041 Contract Administration
Project Completion Process – Defects Notification Period And Final Completion

## Slide 2: List of Topics
Project completion process:
Defects notification period
Final completion

## Slide 3: Project Completion
Practical completion
Defects Notification Period
Final Completion

## Slide 4: Defects Notification Period

## Slide 5: Defects Notification Period
Contractor starts work
Practical
Completion
Actual Contract Period
Final
Completion
Defects Notification Period

## Slide 6: Defects Notification Period
The defects notification period is the period the contractors is liable for the latent defects.
  Patent defects are those which can be discovered by reasonable inspection.
  Latent defects are those which cannot be discovered by reasonable inspection; for example, problems with foundations which may not become apparent for several years after completion when settlement causes cracking in the building.

## Slide 7: Defects Notification Period
The Defects Notification Period shall be 3 Months, Unless some other period is stated in the Special Conditions of Contract (NZS3910, clause 11.2.1)
Beside 3 Months Defect Notification Period, a 12 Months period is typically used, when service installations include an air conditioning system which has to be balanced in both summer and winter conditions.

## Slide 8: Defects Notification Period
The Contractor shall remedy any such defects within 5 Working Days of receipt of the Engineer’s notice (NZS3910, clause 11.2.2)
If the Contractor does not remedy the defects, the Engineer may arrange others to do the work at the Contractor’s Cost (NZS3910, clause 11.2.3)

## Slide 9: Final Completion

## Slide 10: Final Completion
The Engineer shall issue to the Principal and to the Contractor a Final Completion Certificate for the Contract Works or any Separable Portion when in respect of the Contract Works or that Separable Portion:
  The Defects Notification Period has expired; and
  The Contractor has remedied all minor omissions and defects and all defects notified by the Engineer.
---(NZS3910 S11.3.1)

## Slide 11: Final Completion
After issue of Final Completion Certificate:
All outstanding payments are agreed and made.
Any retentions balance is released
In spite of the issue of the Final Completion Certificate, the Contractor shall remain liable for the fulfilment of any obligation of the Contractor under the Contract which then remains unperformed or not properly performed.

## Slide 12: Patent Defects and Latent Defects

## Slide 13: Definitions
Patent defects are those which can be discovered by reasonable inspection. At the date of practical completion the work should be complete and free from patent defects
Latent defects are those which cannot be discovered by reasonable inspection, which can be concealed for many years.

## Slide 14: Patent and Latent Defects
At the date of practical completion the work should be complete and free from patent defect.
Defects Notification Period
Date of issuing Practical Completion Certificate
Latent defect has been concealed in the works and may not become apparent for many years.
Date of issuing Final Completion Certificate
10 years after the date of issuing code Compliance Certificate
10 years remedial period of latent defects. (Building Act 2004 S393)

## Slide 15: THE END