## Slide 1: CIBC6041 Contract Administration
Final Account

## Slide 2: Project Payment Process (Recap)

## Slide 3: Construction Project Payments Process
Commencement of Contract Works
Practical
Completion
Actual Contract Period
Final
Completion
Defects Notification Period
Advance Payment (Optional)
Progress Payment
Practical Completion (portion of Retention Release)
Final Account Settlement

## Slide 4: Final Account Basics

## Slide 5: Final Account - Definition
A Final Account in construction contracts is the agreed statement of the amount of money to be paid at the end of a building contract by the principal to the contractor.
A Final Account is a summary of the financial effect of all activities carried out under the Contract.

## Slide 6: Structure of Final Account

## Slide 7: Structure of final account
Final
Contract Cost
Original Contract amount
Reimburse-ment from/to Principal
Cost fluctuation
Included Sum
variations
Adjusted Cost
To be adjusted when settling final account.

## Slide 8: Types of Variation
Variation
Direct Variation (changes to contract work & contractor performance)
Indirect Variation (treated “as if” Variation)- arising of circumstance that allows contract price to be adjusted

## Slide 9: Variation
Variations
Adjustment of quality
Adjustment of quantity
Change of conditions
Provide substitute
Less quantity
More quantity

## Slide 10: Valuation of Variation
Use base Schedules of Quantities rate.
Use base Schedules of Quantities rate, and adjust for different conditions.
Use daywork rate
Use fair market rate

## Slide 11: Included Sum
Final
Contract Cost`
Original Contract amount
Reimburse-ment from/to Principal
Cost fluctuation
Included Sum
variations
Prime Cost
Provisional Sum
Contingency

## Slide 12: Included Sum – Provisional Sum
Provisional Sum is included in Schedules of Quantities (SOQ) for items of work which cannot be fully described or measured at the time of tendering.
Adjustment methodology:
Deduct estimated provisional sums
Add value of work carried out against provisional sums
-- NZS3910:2013 S12.9.3

## Slide 13: Included Sum –Prime Cost
Adjustment methodology:
Nominated Subcontractors
Deduct estimated prime cost
Contractor
Add contractor’s margin
Add subcontractor’s actual costs
Deduct estimated prime cost
Add contractor’s actual costs
Add contractor’s margin
Add subcontractor’s margin
No deduction of cash discount for early payment.
(NZS3910 S12.11.3)

## Slide 14: Included Sum –Contingency Sum
Contingency Sum may be provided for any work by the contractor, but the expenditure on which is unknown at the time of calling tenders.
Adjustment methodology:
All work carried out under a contingency sum shall be a Variation. The contingency sum shall be deducted from the Contract Price.
--(ANZSMM:2018), (NZS3910:2013 S12.12.2)

## Slide 15: Reimbursement
reimbursement
To Principal
From principal

## Slide 16: Reimbursement from/to Principal
Adjustment Methodology:
Add: Reimbursement from principal
  Any amounts payable by the principal relating to statutory fees and charges, opening up and testing, royalties and patent rights, and insurances;
  reimbursement for contractor’s direct loss/and or expense arising from matters materially affecting the regular progress of the works [NZS3910 clause 9.3.14]
  Bonus of early completion (if specified in the Special Conditions of Contract) [NZS3910 clause 10.6.1]

## Slide 17: Reimbursement from/to Principal
Adjustment Methodology:
Deduct: Reimbursement to principal
  Any amounts payable to the principal relating to loss and expense incurred by the Contractor when it is caused by acts for which the Contractor or his agents are responsible.
  Liquidated damages as specified in the Special Conditions of Contract [NZS3910 clause 10.5]

## Slide 18: Cost Fluctuation
The amounts payable by the Principal to the Contractor under the Contract shall be adjusted up or down by indexation:
(NZS3910`:2013)
Valuation of work
Change of labour Cost Index
Change of produce Cost Index

## Slide 19: Final Account Documents

## Slide 20: Final Account Documents
final payment claim
prepared by the Contractor.
Not later than 1 Month after the issue of the Final Completion Certificate or within such further time as the Engineer may reasonably allow [NZS3910 S12.4.1].

## Slide 21: Final Account Documents
final payment schedule
prepared by the Engineer.
Engineer provides Final Payment Schedule to Contractor; copy to Principal (NZS3910, S12.5.1)
If a Final Payment Schedule cannot be provided, Engineer issues explanatory statement and certificate in form of a Progress Payment Schedule (NZS3910, S12.5.6).

## Slide 22: Final Account Settlement
Structure of final account payment schedule:
Original contract value
+) contract adjusted sum (refer slides 10-21)
=) final adjusted contract value
-) retention $0
=) total payment to date
-) previous payment
=) amount now due (excluding GST)
+) GST
=) amount now due (including GST)

## Slide 23
Conditional payment provisions ineffective
(1) A conditional payment provision of a construction contract has no legal effect and accordingly—
  (a) is not enforceable in any civil proceedings; and
  (b) may not be used as a basis for withholding progress payments that are due and payable under the contract.
  --Construction Contract Act 2002, S13.1

## Slide 24: Reference
Construction Contract Act 2002
NZS3910:2013 Condition of Contract For Building And Civil Engineering Construction.

## Slide 25: THE END