# Project  -  Waterview Fire Station

# 27 March 2018

You are tasked with putting together a competitive tender for this project. At this stage, the tender price should include a P&G and margin based on the overall project and for three trades as follows:

1. Floor Coverings

2. Plasterboard Linings

3. Roofing

P&G

Your contract manager believes that there is no more than 9 months’ work in total on this project.  Between the two of you, you have decided that:

- Scaffolding will be required from the beginning of month 3 – the end of month 8. Estimated cost is $2,500 per week. Erection and dismantling costs $3,000 each.

- Both the project manager and senior QS will be involved a max of 25% of the time.  They are each on a salary of $135,000 per annum

- The site manager and junior QS will be based on site full time.  Their salaries are $95,000 and $65,000 respectively

- Mobile phones are charged at $100/month per staff member

- A site shed, lunchroom and a toilet block will be provided full time. The company owns these, but you need to allow for transport of $400 each way per building.

- Site fencing along the road frontage and a lockable gate will be required.  All other sides are built out. Hire rate is $0.50 per meter per week. Erection and Dismantling is $100 each. Lockable gate is $250.

- A contractors bond [5% of the contract value] is required

- All carnage/mobile access to be priced by the respective subbies

- Any other P&G items will need to be allowed for as, along with head office overheads – say between 3-5% of the contract value

Margin

Allow for a suitable margin

Conditions of Contract

Engineer to Contract:	Mr. Green

The Principal:				Waterview Fire Brigade

Conditions of Contract:			NZS 3910: 2013

Public Liability Insurance:			$10,000,000.00

Contract Works Insurance:			By The Principal

Contract Works Insurance Deductible:	$5,000.00 deductible by responsible party.

Construction Machinery Insurance:	Required for each item that has a market value of more than $25,000.00

Motor Vehicle Third Party Liability:	$5,000,000.00

Retentions:	10%  - Defects Liability retention is 50% of 10%

Defects Liability Period:	12 Months

Tender Validity Period:	1 Month

Payment Claims:	Shall be submitted by the 25th of the month, claims submitted after that date shall not be processed until the month following.

TRADE SPECIFICATION

Roofing

- 0.55 BMT Dimond Trimdeck Coloursteel T2Z Roofing

- GB Antiblaze building foil

- Galvanised safety netting

- Galvanised  steel purlins

- Powdercoated gutters

- PVC Downpipes

Flooring

- Carpet:	 Shaw Pacific heavy duty carpet tiles.

- Underlay: Classic underlay

- Vinyl: Tarkett 2mm thick non slip vinyl

- Coved turn up 100mm high in all wet areas.

Painting

- Internal: Resene Waterborne semi-gloss paint system 1 x undercoat 2 x topcoats

- Paint colour TBC